## version discription
version | comment
version 1 | application in up
version 2 | the main functions working
version 3 | clean code and prepare documentation
ready for release and publish in playstore

## task list
task list | category | periority | type | version
select files with normalized filter in which exactly one instance for any kind of property is included | userquery | 2 | major | 2.0.0
implement XGboost method for training model | userquery | 2 | major
forget password | webapp | 2 | minor | 2.1.0
send email to user | webapp | 2 | minor
handle user request (area) | userquery | 2 | minor | 2.2.0
prepare a list of locations | web scrape | 2 | minor | 2.3.0
webservice to send list of locations to application | web scrape | 2 | minor
https://stackoverflow.com/questions/46385350/django-cron-task-not-executing-automatically | Server Side | 3 | major | 3.0.0
how to upload website on server | Server Side | 3 | major
autentication is complosory for sending request | userquery | 3 | minor | 3.1.0
use sklearn normalize method for enhance prediction | userquery | 3 | minor | 3.2.0
in cleaning database consider that for each location there should be at least 50 records left | clean database | 3 | minor | 3.3.0
extra data (more that 150 for each location will be deleted) | clean database | 3 | minor
if last update was not successfull try again some minutes later | clean database | 3 | patch | 3.3.1
start cron from admin panel | admin | 3 | minor | 3.4.0
some setting and tresholds should be managed in admin panel | admin | 3 | minor
upgrade recaptcha | webapp | 3 | minor | 3.5.0
make configs hidden | webapp | 3 | patch | 3.5.1
convert scrape type to choice | web scrape | 3 | patch | 3.5.2
fix bug: scrape age (new/none) is not detected | web scrape | 3 | patch | 3.5.3
fix warning of ssl sending request to ihome | web scrape | 3 | patch | 3.5.4
ask user if prediction was accurate or not (receive and store poll) | poll | 3 | minor | 3.6.0